## Cover
KAZ PP EXPANSION PROJECT ¦ EHS MANAGEMENT SYSTEM
Integrated Occupational Health, Safety & Environment Control Workbook ¦ OSHA KPIs ¦ Confidential
| SYSTEM IDENTITY |  | QUICK STATUS
| Project Name | KAZ PP Expansion Project | Today
| Client / Owner | As per Contract | File Rev | 00
| Main Contractor | Team Seisms / Team Al-Mayal Consortium | Macro Pack | Import VBA_EHS_Module.bas
| Document Title | Integrated EHS Management & Evaluation System | Language | EN / AR bilingual labels
| Document No. | KAZ-EHS-SYS-001 Rev.00
| Classification | CONFIDENTIAL — Controlled Document
| Prepared by | EHS Department — Project Control
| Admin Owner | EHS Manager (Full Control)
| Effective Date | 2026-01-01
| Workbook Password (Admin) | KAZ-EHS-ADMIN-2026
WORKSHEET MAP ¦ هيكل الشيتات
| Sheet | Purpose / الغرض
| 00_Cover | الغلاف والتعريف والصلاحيات
| 01_Dashboard | لوحة التحكم ومؤشرات OSHA / KPIs
| 02_ManHours | حاسبة ساعات العمل اليومية (Seisms / Al-Mayal)
| 03_Incidents | سجل الحوادث والإصابات و Near Miss
| 04_Observations | تتبع الملاحظات + Aging + PTW
| 05_NCR | إخطارات عدم المطابقة NCR
| 06_Scorecard | تقييم أداء المقاولين الثانويين
| 07_CAPA_AI | محور تحويل الملاحظات والإجراءات التصحيحية
| 08_Training | مصفوفة شهادات العمالة الماهرة
| 09_Equipment | تفتيش المعدات الثقيلة وشهادات الطرف الثالث
| 10_Documents | مستودع الوثائق والسير الذاتية والخطط
| 11_Lookups | قوائم التصنيف والمعايير (لا تعدّل المعادلات)
| 12_Admin | إعدادات النظام، الأهداف، البريد، الحماية
OSHA FORMULAS USED IN THIS SYSTEM
LTIFR (Lost Time Injury Frequency Rate) = (Number of LTIs × 1,000,000) / Total Man-Hours
TRIFR (Total Recordable Injury Frequency Rate) = (Recordable Cases × 1,000,000) / Total Man-Hours
Severity Rate (optional) = (Lost Workdays × 1,000,000) / Total Man-Hours
Man-Hours without LTI = Cumulative man-hours since last LTI date (auto from 02_ManHours & 03_Incidents)
SECURITY: Protect workbook & sheets with the Admin password shown above. Yellow cells = INPUT (unlocked). Blue cells = CALCULATED (locked). Import VBA_EHS_Module.bas via Alt+F11 → File → Import. Enable macros. Outlook must be installed for email alerts. Default password: KAZ-EHS-ADMIN-2026 — change it immediately after first open.

## Dashboard
01 ¦ EHS DASHBOARD & KPIs — KAZ PP EXPANSION PROJECT
Live OSHA rates, man-hours without LTI, case counters, observation aging, contractor scores. Calculated cells are locked.
| Report date |  | Total Man-Hours |  | Last LTI
| MAN-HOURS w/o LTI |  |  | LTIFR |  | TRIFR |  | EHS PERFORMANCE SCORE |  | PERFORMANCE BAND
| Target LTIFR |  |  | vs Target |  | vs Target
CASE & OBSERVATION COUNTERS (auto from registers)
| Near Miss |  | Unsafe Acts |  | Unsafe Conditions |  | First Aid |  | Recordable | LTI
| NCR Open |  | OBS Open |  | OBS Overdue |  | OBS Critical open |  | Cert Expired/Crit. | Equip Quarantine+
| MAN-HOURS SPLIT | [5 empty] | TOP OVERDUE OBSERVATIONS (aging)
| Team Seisms |  | Team Al-Mayal |  |  |  | Use sheet Observations, sort by Overdue Days. Open items escalate every calendar day until Closed.
| Indirect |  | Unified Total
LIFE-SAVING FOCUS AREAS (from observation types — count)
| Type | Count
Lifting Operations
Working at Height
Excavation
Scaffolding
Confined Space
Electrical
Work Permits / PTW
MACRO ACTIONS (after importing VBA_EHS_Module.bas): EHS_SendCriticalAlert ¦ EHS_SendNCRAlert ¦ EHS_ExportWeeklyPDF ¦ EHS_ProtectAll ¦ EHS_UnprotectAll ¦ EHS_RefreshAging

## Lookups
11 ¦ LOOKUP TABLES & CLASSIFICATIONS
Do not delete named lists. Used by data validation across the workbook.
| Observation Types | Status | Severity | Subcontractors | Incident Class | Trade / Certificate Type | Equipment Type | Teams | Shift
| Lifting Operations | Open | Low | Team Seisms | Near Miss | Crane Operator | Mobile Crane | Team Seisms | Day
| Confined Space | In Progress | Medium | Team Al-Mayal | Unsafe Act | Rigger / Banksman | Tower Crane | Team Al-Mayal | Night
| Excavation | Closed | High | Civil Subcontractor A | Unsafe Condition | First Aider / EMT | MEWP / Manlift | Shared / Indirect | Double
| Scaffolding | Overdue | Critical | Mechanical Subcontractor B | First Aid | Welder | Forklift
| Working at Height |  |  | Electrical Subcontractor C | Medical Treatment (MTC) | Scaffolder | Excavator
| Electrical |  |  | Scaffolding Contractor D | Restricted Work (RWC) | Electrician | Loader
| Work Permits / PTW |  |  | Lifting Contractor E | Lost Time Injury (LTI) | Confined Space Entrant | Dump Truck
| Hot Work |  |  | Security Contractor F | Recordable Case | H2S / BA User | Generator
| Housekeeping |  |  |  | Property Damage | Forklift Operator | Compressor
| PPE |  |  |  | Environmental Incident | Excavator Operator | Welding Machine
| Traffic / Vehicles |  |  |  | Security Incident | Fire Watch | Scaffold Tower
| Chemical / HAZMAT |  |  |  | Fatality | EHS Officer | Lifting Gear (slings/shackles)
| Fire Prevention |  |  |  |  | EHS Supervisor
| Environmental |  |  |  |  | EHS Manager
| Security |  |  |  |  | PTW Receiver
| Welfare |  |  |  |  | Authorized Gas Tester
Barricades / Signage
Tools & Equipment
Energy Isolation / LOTO
Other
Risk Matrix Score (S×L)
Likelihood 1-5 × Severity 1-5. Score >=15 Critical, >=10 High, >=5 Medium, else Low.

## Admin
12 ¦ SYSTEM ADMINISTRATION & TARGETS
Yellow = editable settings. Used by Dashboard, Scorecard, VBA email and PDF export.
| PARAMETER | VALUE | NOTES
| Project Title | KAZ PP Expansion Project | Shown on reports
| Hours per worker per day (default) | 10 | Used if shift hours blank
| OSHA multiplier | 1000000 | Do not change (OSHA 200,000 optional)
| LTIFR Target | 0 | Project target
| TRIFR Target | 1.5 | Project target
| Observation close-out SLA (days) | 7 | Aging overdue after this
| Critical observation SLA (days) | 1 | 1 day — stored as 1
| Certificate warning (days) | 30 | Conditional formatting
| Certificate critical (days) | 7 | Red alert
| NCR close-out SLA (days) | 14
| Scorecard: points per Open obs | -2 | Negative
| Scorecard: points per Overdue obs | -5
| Scorecard: points per NCR | -8
| Scorecard: points per LTI | -25
| Scorecard: points per Recordable | -15
| Scorecard: points per Near Miss (positive reporting) | 1 | Encourage reporting
| Scorecard starting points | 100 | Baseline
| Minimum score floor | 0
| Outlook To (Project Management) | pm@kaz-pp.example; ehs.manager@kaz-pp.example | Semicolon separated
| Outlook CC (EHS) | ehs.team@kaz-pp.example
| Send mail on Critical Incident | YES | YES/NO
| Send mail on new NCR | YES | YES/NO
| Weekly report folder path | C:\EHS_Reports\KAZ_PP | PDF export path
| OpenAI API Key (optional) |  | Leave blank to use local CAPA engine
| OpenAI Model | gpt-4o-mini | If API used
| Admin password hint | See Cover sheet I14 / C14 | Never share
| Last LTI Date (override if needed) |  | Leave blank to auto from Incidents
| Site location | KAZ PP Site
PROJECT EHS PERFORMANCE BANDS (used on Dashboard)
|  | From score | Band
| Excellent | 90 | A — Excellent (Green)
| Satisfactory | 75 | B — Satisfactory
| Needs Improvement | 60 | C — Needs Improvement
| Unsatisfactory | 0 | D — Unsatisfactory / Stop Work review
VBA BUTTONS (after importing .bas): Alt+F8 → EHS_SendCriticalAlert / EHS_ExportWeeklyPDF / EHS_ProtectAll / EHS_UnprotectAll / EHS_RefreshAging / EHS_FormatObservation

## ManHours
02 ¦ DAILY MAN-HOURS CALCULATOR
Input daily headcount for Team Seisms and Team Al-Mayal. One consolidated total in cell P4 (and Dashboard).
| CONSOLIDATED PROJECT TOTAL MAN-HOURS |  |  | Hours / worker default → |  | ONE CELL — TOTAL MAN-HOURS (ALL DAYS, BOTH TEAMS) |  |  |  |  | Seisms Σ
| Σ Seisms MH |  | Σ Al-Mayal MH |  | Σ Indirect |  | GRAND TOTAL (unified cell) |  |  |  | This I5 is the single consolidated man-hours output used by Dashboard KPIs.
Yellow = input headcount. Blue = calculated man-hours. Copy formulas down as the project continues.
| Date | Day | Shift | Seisms Headcount | Seisms Hrs/person | Seisms Man-Hours | Al-Mayal Headcount | Al-Mayal Hrs/person | Al-Mayal Man-Hours | Indirect / Visitors | Indirect Hours | DAILY TOTAL MH | Remarks | Entered by | Weather / Notes
| 2026-03-01 |  | Day | 85 | 10 |  | 70 | 10 |  | 8 |  |  |  | EHS
| 2026-03-02 |  | Day | 88 | 10 |  | 72 | 10 |  | 8 |  |  |  | EHS
| 2026-03-03 |  | Day | 91 | 10 |  | 74 | 10 |  | 8 |  |  |  | EHS
| 2026-03-04 |  | Day | 94 | 10 |  | 76 | 10 |  | 8 |  |  |  | EHS
| 2026-03-05 |  | Day | 97 | 10 |  | 70 | 10 |  | 8 |  |  |  | EHS
| 2026-03-06 |  | Day | 85 | 10 |  | 72 | 10 |  | 8 |  |  |  | EHS
| 2026-03-07 |  | Day | 88 | 10 |  | 74 | 10 |  | 8 |  |  |  | EHS
| 2026-03-08 |  | Day | 91 | 10 |  | 76 | 10 |  | 8 |  |  |  | EHS
| 2026-03-09 |  | Day | 94 | 10 |  | 70 | 10 |  | 8 |  |  |  | EHS
| 2026-03-10 |  | Day | 97 | 10 |  | 72 | 10 |  | 8 |  |  |  | EHS
| 2026-03-11 |  | Day | 85 | 10 |  | 74 | 10 |  | 8 |  |  |  | EHS
| 2026-03-12 |  | Day | 88 | 10 |  | 76 | 10 |  | 8 |  |  |  | EHS
| 2026-03-13 |  | Day | 91 | 10 |  | 70 | 10 |  | 8 |  |  |  | EHS
| 2026-03-14 |  | Day | 94 | 10 |  | 72 | 10 |  | 8 |  |  |  | EHS

## Incidents
03 ¦ INCIDENT & CASE REGISTER (OSHA CLASSIFICATION)
Record Near Miss, Unsafe Acts/Conditions, First Aid, Recordable, LTI. Feeds Dashboard counters and rates.
KPI COUNTERS (auto) — Near Miss ¦ Unsafe Act ¦ Unsafe Condition ¦ First Aid ¦ Recordable ¦ LTI ¦ Open cases
| INC-ID | Date | Time | Classification | Location / Area | Subcontractor | PTW No. | Injured / Involved | Body Part | Lost Days | Recordable? (Y/N) | LTI? (Y/N) | Description | Immediate Action | Root Cause | Status | Investigation Lead | Closed Date | Severity | COUNTERS
| INC-001 | 2026-03-02 | 08:40 | Near Miss | Unit 2 Pipe Rack | Team Seisms | PTW-0142 | N/A |  | 0 |  |  | Load swung within 2m of live line during tandem lift | Stop work, re-plan lift | Inadequate exclusion zone | Closed | EHS Off. Ali | 2026-03-03 | High | Near Miss
| INC-002 | 2026-03-05 | 14:15 | Unsafe Condition | Excavation Grid C | Team Al-Mayal | PTW-0188 | N/A |  | 0 |  |  | Excavation >1.2m without shoring / ladder | Barrier + backfill temporary | PTW controls not implemented | Closed | EHS Off. Omar | 2026-03-06 | High | Unsafe Act
| INC-003 | 2026-03-08 | 11:05 | First Aid | Workshop | Mechanical Subcontractor B | PTW-0210 | Worker #442 | Hand | 0 |  |  | Minor cut while using utility knife without cut-resistant glove | First aid, replace glove | PPE gap | Closed | Nurse | 2026-03-08 | Low | Unsafe Condition
| INC-004 | 2026-03-10 | 16:20 | Unsafe Act | Scaffold Bay 4 | Scaffolding Contractor D | PTW-0225 | N/A |  | 0 |  |  | Worker climbing scaffold without harness attached | Stopped, TBT refresh | Behavior / supervision | Open | EHS Sup. Hassan |  | Medium | First Aid
Recordable
LTI
Fatalities
Open
Last LTI Date
Lost days sum

## Observations
04 ¦ OBSERVATION TRACKER & AGING SYSTEM
Overdue Days escalate daily while status is Open / In Progress. Frequency Count = repeats of same type + area + contractor.
| OBS-ID | Date | Type | Severity | Status | Subcontractor | PTW Number | Location / Area | Observation (raw) | Immediate Action | Action Owner | Target Close | Closed Date | Overdue Days | Frequency Count | Repeat Flag | Reported by | NCR Linked | Risk Score | OBS KPIs
| OBS-001 | 2026-03-01 | Lifting Operations | High | Closed | Lifting Contractor E | PTW-0101 | Laydown A | Tag line not used on 12t load | Stop lift, toolbox | Lift Sup. | 2026-03-02 | 2026-03-02 |  |  |  | Ahmed |  |  | Total
| OBS-002 | 2026-03-03 | Working at Height | Critical | Open | Team Seisms | PTW-0155 | Boiler roof | Unprotected edge 8m, no harness anchorage | Barrier 2m, stop work | Site Eng. | 2026-03-04 |  |  |  |  | Sara |  |  | Open
| OBS-003 | 2026-03-04 | Excavation | High | In Progress | Team Al-Mayal | PTW-0160 | Grid B-4 | Spoil stored at edge of 2.1m trench | Move spoil 1m, shore | Civil Sup. | 2026-03-06 |  |  |  |  | Omar |  |  | In Progress
| OBS-004 | 2026-03-06 | Work Permits / PTW | Medium | Open | Electrical Subcontractor C | PTW-0172 | Substation | PTW expired, work continuing | Stop, reissue PTW | EA | 2026-03-07 |  |  |  |  | Hassan |  |  | Closed
| OBS-005 | 2026-03-07 | Scaffolding | High | Open | Scaffolding Contractor D | PTW-0180 | Pipe rack 3 | Incomplete scaffold — no toe boards, green tag on red | Red tag, dismantle | Scaffold I | 2026-03-08 |  |  |  |  | Ali |  |  | Overdue (days>0)
| OBS-006 | 2026-03-08 | Lifting Operations | Medium | Closed | Lifting Contractor E | PTW-0184 | Laydown A | Out of date color code on sling | Quarantine sling | Store | 2026-03-09 | 2026-03-09 |  |  |  | Ahmed |  |  | Critical open
| OBS-007 | 2026-03-09 | Electrical | High | In Progress | Electrical Subcontractor C | PTW-0190 | MCC room | Panel open, no electrical barrier, live | Isolate, LOTO | Elec Sup. | 2026-03-10 |  |  |  |  | Nour
| OBS-008 | 2026-03-10 | Confined Space | Critical | Open | Mechanical Subcontractor B | PTW-0199 | Tank T-12 | Entry without gas test / attendant | Evacuate, CS procedure | EHS Mgr | 2026-03-10 |  |  |  |  | Sara
Formulas:
Overdue Days = IF([Date]="","",IF(OR([Status]="Closed",[Status]=""),0,IF([Closed Date]<>"",MAX(0,[Closed Date]-[Target Close]),MAX(0,TODAY()-IF([Target Close]="",[Date]+IF([Severity]="Critical",Admin!$C11,Admin!$C10),[Target Close])))))

## NCR
05 ¦ NON-CONFORMANCE REPORTS (NCR)
New NCR can trigger Outlook email via VBA (EHS_SendNCRAlert). Links to subcontractors scorecard.
| NCR-ID | Date | Subcontractor | Source (OBS/INC) | Finding | Required Action | Owner | Priority | Target Date | Closed Date | Status | Days Open | Issued by | Related PTW | Open NCRs
| NCR-001 | 2026-03-04 | Team Seisms | OBS-002 | Unprotected edge WAH — systemic PTW failure | Revise WAH permit checklist; retrain crew; barrier standard | Construction Mgr | Critical | 2026-03-11 |  | Open |  | EHS Manager | PTW-0155
| NCR-002 | 2026-03-10 | Mechanical Subcontractor B | OBS-008 | Confined space entry without atmospheric test | Stop CS work; full CS procedure rollout; competency cards | Mech PM | Critical | 2026-03-17 |  | Open |  | EHS Manager | PTW-0199

## Scorecard
06 ¦ SUBCONTRACTOR EHS SCORECARD
Automatic scoring from Observations, Incidents and NCRs. Baseline 100. Floor = Admin minimum.
| Subcontractor | Open OBS | Overdue OBS | Total OBS | NCRs | LTI | Recordable | Near Miss | First Aid | Raw Penalty/Bonus | SCORE /100 | Band | Trend / Comment
Scoring model: Start at Admin!C21 (default 100). Open OBS, Overdue, NCR, LTI, Recordable subtract points. Near Miss reporting adds points (positive reporting culture).

## CAPA_AI
07 ¦ AI CORRECTIVE ACTION & CONVERSION HUB
Paste raw notes in column C. VBA EHS_FormatObservation converts to official EHS wording + CAPA. Optional OpenAI API in Admin!C28.
HOW TO USE
1) Enter RAW note in C (yellow). 2) Select the row and run macro EHS_FormatObservation (or click after importing VBA). 3) Column D receives official bilingual-style EHS observation. Column E receives CAPA (Corrective & Preventive). 4) If Admin API key is blank, a built-in rule engine (keywords: lift, scaffold, excav, confined, electrical, PTW, height, PPE) is used. 5) Copy D/E into Observations tracker.
| CAPA-ID | RAW NOTES (input) | FORMATTED EHS OBSERVATION (output) | CAPA — Corrective & Preventive Action (output) | Suggested Type | Suggested Severity | Push status
| CAPA-001 | guys working on roof no harness and edge open next to boiler |  |  |  |  | Draft
| CAPA-002 | excavator digging beside live 11kv cable no spotter ptw not on site |  |  |  |  | Draft
| CAPA-003 | sling colour code expired and tag line missing tandem lift |  |  |  |  | Draft
| CAPA-004 | confined tank someone went in no gas test no standby man |  |  |  |  | Draft
| CAPA-005 | scaffold green tag but no toeboard and missing ties |  |  |  |  | Draft

## Training
08 ¦ TRAINING & COMPETENCY MATRIX (SKILLED LABOUR)
Conditional colour: GREEN valid ¦ AMBER ≤30 days ¦ RED ≤7 days or expired. Warning window = Admin!C12.
| EMP-ID | Full Name | Badge / ID | Trade / Certificate | Employer | Cert No. | Issue Date | Expiry Date | Days to Expiry | Status | Provider / 3rd Party | Refresh due | Remarks | Expired / Critical count
| EMP-001 | Mohammed Al-Farsi | KAZ-1021 | Crane Operator | Lifting Contractor E | CO-8891 | 2025-06-01 | 2026-06-01 | [5 empty] | Warning ≤30d
| EMP-002 | Yousef Nasser | KAZ-1022 | Rigger / Banksman | Lifting Contractor E | RG-4410 | 2025-04-10 | 2026-04-10
| EMP-003 | Fatima Saleh | KAZ-0880 | First Aider / EMT | Team Seisms | FA-2201 | 2025-09-01 | 2026-03-20
| EMP-004 | Karim Haddad | KAZ-1304 | Welder | Mechanical Subcontractor B | W-AWS-77 | 2024-12-01 | 2026-03-15
| EMP-005 | Sami Qasim | KAZ-1502 | Scaffolder | Scaffolding Contractor D | SC-CISRS-19 | 2025-01-15 | 2026-01-15
| EMP-006 | Nabil Othman | KAZ-1110 | Electrician | Electrical Subcontractor C | EL-440 | 2025-07-01 | 2027-07-01
| EMP-007 | Hassan Ibrahim | KAZ-0991 | EHS Officer | Team Seisms | NEBOSH-GC-882 | 2024-05-01 | 2029-05-01
| EMP-008 | Omar Farouk | KAZ-0772 | Authorized Gas Tester | Team Al-Mayal | AGT-12 | 2025-10-01 | 2026-04-01

## Equipment
09 ¦ HEAVY EQUIPMENT INSPECTION & 3RD PARTY CERTIFICATES
Colour alerts 30 days before certificate / inspection expiry. Quarantine if expired.
| Asset ID | Equipment Type | Make / Model | Owner / Contractor | Plate / Serial | 3rd Party Cert No. | Cert Expiry | Days to Cert | Last Inspection | Next Inspection | Days to Insp. | Status | Operator EMP-ID | Remarks
| CRN-01 | Mobile Crane | Liebherr LTM 1100 | Lifting Contractor E | SN-8821 | TPI-CR-2025-09 | 2026-04-15 |  | 2026-03-01 | 2026-03-08
| EXC-04 | Excavator | CAT 336 | Team Al-Mayal | SN-336-12 | TPI-EX-2025-11 | 2026-05-01 |  | 2026-03-05 | 2026-03-12
| MEWP-2 | MEWP / Manlift | JLG 600SJ | Team Seisms | SN-600-77 | TPI-MW-2025-08 | 2026-03-25 |  | 2026-02-20 | 2026-03-06
| GEN-03 | Generator | Cummins 250kVA | Electrical Subcontractor C | SN-CU-250 | TPI-GN-2025-01 | 2026-03-18 |  | 2026-03-01 | 2026-04-01
| FLT-01 | Forklift | Toyota 8FD | Team Seisms | SN-TY-19 | TPI-FL-2025-12 | 2026-12-01 |  | 2026-03-09 | 2026-03-16
Formulas:
Days to Cert = IF([Cert Expiry]="","",[Cert Expiry]-TODAY())
Days to Insp. = IF([Next Inspection]="","",[Next Inspection]-TODAY())

## Documents
10 ¦ DOCUMENT & CV HUB
Hyperlink path or SharePoint/OneDrive URL in column G. EHS staff CVs, HSE Plan, Security Plan, PTW Manual.
| DOC-ID | Category | Title / Name | Owner | Rev | Link / Path (Ctrl+K) | Date | Status | Related Person / Area | Notes
| DOC-001 | HSE Plan | KAZ Project EHS Plan | EHS Manager | 02 | KAZ Project EHS Plan.pdf | 2026-01-15 | Approved | Project-wide
| DOC-002 | Security Plan | KAZ Security Management Plan | Security Lead | 01 | خطه السكيورتي.docx | 2026-01-20 | Approved | Project-wide
| DOC-003 | PTW Manual | Permit to Work System Manual (Final) | EHS Manager | Final | بيرمت سستم (Final).docx | 2026-02-01 | Approved | All workfaces
| DOC-004 | Policy | EHS Policy (EN) | Corporate EHS | — | Annex 1_EHS Policy_en (2).pdf | 2025-06-01 | Approved | Corporate
| DOC-005 | Policy | Quality Policy (EN) | QA | — | Annex 1_SE Quality Policy_en (4).pdf | 2025-06-01 | Approved | Corporate
| DOC-006 | Procedure | EHS General Requirements for Contractors | EHS Manager | EN | Instruction_EHS General Requirements for Contractors_EN.pdf | 2025-08-01 | Approved | Subcontractors
| DOC-007 | Standard | EHS Principles and core responsibilities | Corporate EHS | EN | Standard_EHS Principles and core responsibilities_EN (9).pdf | 2025-05-01 | Approved | All staff
| DOC-008 | Risk | KAZ Project Risk Analysis | EHS Manager | 01 | KAZ Project Risk Analysis.pdf | 2026-01-10 | Approved | Project-wide
| DOC-009 | CV — EHS Staff | EHS Manager CV (place file) | HR / EHS | 00 | CVs\EHS_Manager.pdf | 2026-02-01 | Live | EHS Manager
| DOC-010 | CV — EHS Staff | EHS Officer — Hassan Ibrahim CV | HR / EHS | 00 | CVs\EHS_Officer_Hassan.pdf | 2026-02-01 | Live | EMP-007
| DOC-011 | CV — EHS Staff | EHS Supervisor CV (place file) | HR / EHS | 00 | CVs\EHS_Supervisor.pdf | 2026-02-01 | Live | EHS Supervisor
| DOC-012 | Form | Near-Miss Report Form | EHS | 01 | 000480_Near-Miss Report Form.docx | 2026-01-01 | Approved | Incidents
| DOC-013 | Checklist | EHS Officer Site Checklist | EHS | 01 | EHS Officer site check list.xlsx | 2026-01-01 | Approved | Inspections
| DOC-014 | Report | Daily EHS Report template | EHS | 2026 | Daily EHS Report 2026.xlsx | 2026-01-01 | Approved | Daily
| DOC-015 | Materials | Materials Management Plan (Final) | Logistics | Final | خطه اداره المواد (Final).docx | 2026-02-01 | Approved | Stores
Place actual CV PDF/DOCX files in a folder named CVs next to this workbook, or paste SharePoint links. Select a cell in column G → Insert → Link (Ctrl+K). VBA cannot embed binary files inside xlsx; hyperlinks are the controlled method.