## CU-EHS-S-FO-0029
HSE OFFICER SITE INSPECTION CHECKLIST
Project Name: Kaz Power Plant Upgrade Project |  | Total Number of Employees: 41 |  |  | Start Date:25-aug-2026
Name of the Employer (Customer) : BGC & MOE |  | Number of Siemens Employees: 2 |  |  | Planned Completion Date: 13 MONTH
Number of Subcontractors on the Project and Company Names : AL-MIAL - 39
Summary of Project Scope and Current Status :The audit scope covers the Environmental, Health, and Safety (EHS) management for the Kaz Power Plant Upgrade Project in collaboration with BGC & MoE and subcontractor Al-Mial. The current status involves ongoing consolidation, updating of HSE plans, and documentation of operational safety reviews on-site."
GENERAL ISSUES |  | YES | NO | N/A* | REMARKS
1 | Has an HSE plan been prepared for the project? Is it up to date? |  | ✗ |  | ONLY FROM SE
2 | Has the risk assessment been approved by the risk assessment team? |  | ✗ |  | On going
3 | Is the risk assessment posted in visible places in the work area ? | ✓
4 | Has an emergency plan been prepared? |  | ✗
5 | Are the annexes of the emergency plan posted in visible places ? | ✓
6 | Have employees been given HSE and risk assessment training? |  | ✗
7 | Is there an approved "Site Manager / Site Chief appointment" document? |  | ✗
8 | Is there a full-time HSE officer (HSE O)? (If so, an official assignment document must be available) | ✓
9 | Have the official HSE Manager/Specialist and Site Medical Staff been appointed and approved in accordance with MoE (Ministry of Electricity) safety requirements and Iraqi Labor Law No. 37 of 2015? | ✓
10 | Is there an approved inspection and recommendation logbook for Occupational Health and Safety? | ✓
11 | Is the Occupational Health and Safety inspection and recommendation logbook filled in regularly? | ✓
12 | Has an HSE training plan been prepared? | ✓
13 | Does the Site HSE Committee hold regular meetings (monthly/bi-weekly)? (Applies to project sites with 50 or more workforce | ✓
14 | Has the "Employee Start-of-Work Check" form been applied for all employees? | ✓
15 | Is the vocational competence of the employees adequate? | ✓
16 | Is the number of employees with certified first aid training sufficient? (10% of the employees must be certified first aiders) |  | ✗ |  | Note: There is only one certified paramedic on site. There are currently no fire response officers.
17 | Have the first aid and fire response officers been designated? |  | ✗ |  | Only one paramedic was assigned to the site. No fire response officers were assigned.
18 | Are near-miss and hazardous situation notifications being reported? | ✓
Traffic Signs |  | Yes | No | N/A* | Remarks
1 | Is the site board at the site entrance in a visible place? |  |  |  | Completely invisible at the entrance; installation required.
2 | Are there measures and warning signs at and around the facility entrance to prevent the entry of unauthorised persons ? |  | ✗
3 | Is there a ‘Heavy Vehicles and/or Construction Machinery May Exit’ sign at the facility entrance? Is it in a suitable place, visible and clean ? |  | ✗
4 | Are there signs directing vehicles and pedestrians at the facility entrance and inside ? Are they visible? | ✓
6 | Are there signs showing the speed limit inside the facility? |  | ✗
7 | Are the work and office areas separated from other areas by signs and barriers ? | ✓
Personal Protective Equipment |  | Yes | No | N/A* | Remarks
1 | Does the provided PPE meet approved local/international safety standards (e.g., Iraqi Labor Law / OSHA / ANSI) and remain in good condition?" | ✓
2 | "Are standard safety shoes (with toe protection and anti-puncture soles) provided and worn by all workers?" | ✓
3 | Is a double-lanyard full body (parachute type) safety harness complying with EN 361, EN 358, EN 813 standards used for work at height? |  |  | N/A
4 | Is an EN 166 face shield used during work with an angle grinder? |  |  | N/A
5 | Have the personnel been informed not to wear rings, necklaces and similar jewellery during work ? | ✓
6 | Is the full body (parachute type) safety harness anchored to solid points? |  |  | N/A
7 | Are the full body (parachute type) safety harness and its accessories in good condition? (The harness must not be more than 3 years past its production date) |  |  | N/A
Electrical Work and Use of Electrical Equipment |  | Yes | No | N/A* | Remarks
1 | Are there electrical hazard warning signs on the electrical panels ? | ✓
2 | Is an "Electrical Work Permit" used for electrical work? |  |  | N/A
3 | Do the personnel working on electrical jobs have the required vocational competence? (Electrical engineer/technologist, electrical technician, master electrician) |  |  | N/A
4 | Do the hand tools used in electrical work comply with the EN 60900 standard ? (1000 V insulated) |  |  | N/A
5 | Is an arc flash resistant and electrically insulated set used? |  |  | N/A
6 | Is there an insulating mat in front of the electrical panels? |  |  | N/A
7 | Are the on / off switches on the equipment clearly marked? | ✓
8 | Do the portable extension cords used have armoured protectors? Is the insulation of the cables adequate? |  |  | N/A
9 | Are the mains-powered and battery-powered electrical equipment inspected and tagged? | ✓
10 | Is there a residual current device on the portable site electrical panels? (30 mA) |  |  | N/A
11 | Has the earthing measurement been carried out on the portable site electrical panels and on the electrical installation in the site office area? (Once a year) |  | ✗
12 | Is there an emergency stop button on the portable site electrical panels? | ✓
Chemical Materials and Waste |  | Yes | No | N/A* | Remarks
1 | Are chemicals used on site? If used, are the "Material Safety Data Sheets" (MSDS) of the chemicals available? |  |  | N/A
2 | Are flammable chemicals stored separately? |  |  | N/A
3 | Has a designated area been established for hazardous materials and waste? |  |  | N/A
4 | Is the waste generated on site segregated according to its source? |  |  | N/A
Construction Machinery and Passenger Vehicles |  | Yes | No | N/A* | Remarks
1 | Is the Siemens "Crane Work Permit" actively used for lifting machinery (crane, hiab and work platform) ? |  |  | N/A
2 | Is the quarterly periodic inspection report of the construction machine available? | ✓
3 | Do the construction machines have a reversing warning alarm? (Audible and visual) | ✓
4 | Does the heavy equipment operator hold a valid Iraqi Heavy Driving License and an accredited Third-Party Operator Competency Card, with copies archived on site?" | ✓
5 | Are the registration and traffic inspection documents of the construction machine available? | ✓
6 | "Have passenger vehicles been serviced? Are they equipped with a first aid kit, fire extinguisher, and valid spare tire with good overall tire conditions?" | ✓
Storage Areas |  | Yes | No | N/A* | Remarks
1 | Has the storage area been defined? | ✓
2 | Are the shelves in the storage area fixed to the wall? | ✓
3 | Are the cable drums placed on level ground and supported with chocks? |  |  | N/A
4 | Are there enough ABC class dry chemical fire extinguishers in the storage area? (One 6 kg extinguisher per 250 m²) | ✓
5 | Has a safe stacking limit been defined in the storage area and are the materials stacked accordingly? (Maximum stacking height 2 m) | ✓
6 | Is the storage area fenced off? Are warning signs available? | ✓
Common Use Areas |  | Yes | No | N/A* | Remarks
1 | Is the site office clean? | ✓
5 | Do the waste bins used have lids and are the lids kept closed? | ✓
7 | Are the utility water and the drinking water separate? | ✓
9 | Are the changing rooms clean? | ✓
10 | Is the temperature of the changing room appropriate? | ✓
11 | Is there any broken equipment in the changing room requiring repair? |  | ✗ |  | "One of the air conditioning units in the changing rooms is broken and requires immediate maintenance."
12 | Are the toilets cleaned regularly? | ✓
13 | Have the defects requiring repair in the toilets been rectified? | ✓
14 | Are there enough washbasins, liquid soap and lidded waste bins for personal hygiene? | ✓
15 | Is there a "Not Drinking Water" warning sign for the utility water? |  | ✗
16 | Are the showers clean? |  |  | N/A
17 | Is there hot water? |  |  | N/A
18 | Have the defects requiring repair in the showers been rectified? |  |  | N/A
19 | Are there warning signs regarding slippery floors that create a risk of falling? |  | ✗
Emergencies |  | Yes | No | N/A* | Remarks
1 | Is an emergency plan available? |  | ✗
2 | Have the emergency response teams been designated and announced? | ✓
3 | Has an assembly point been designated? | ✓
4 | Is there a list showing the locations and quantities of the fire extinguishers on site? |  | ✗
5 | Is there a first aid kit ? Is the equipment inside it adequate? | ✓
6 | Are there first aid certified personnel and are first aider stickers affixed to their helmets? | ✓
7 | Has the nearest health institution been identified and its contact details obtained? |  | ✗
8 | Is there a first aid cabinet sign outside the area where the first aid cabinet is located? |  | ✗
9 | Are there any items with an expired shelf life inside the first aid cabinet? |  |  | N/A
Fire Extinguishers |  | Yes | No | N/A* | Remarks
1 | Is a fire extinguisher available? Is the number sufficient? |  |  |  | On going
2 | Are the lead seals on the pins of the fire extinguishers in place? | ✓
3 | Is the pressure gauge normal ? (Is the needle in the green zone?) | ✓
4 | Are there labels on them showing the last inspection and refill dates? | ✓
5 | Have the inspection and refilling operations been carried out on time? (Check whether the inspection date has passed) | ✓
6 | Are the cylinder body, valve and pressure gauge in normal condition? (Check whether there is any crack or impact mark) | ✓
7 | Is it placed so that it can be easily reached ? (Check whether there is any material in front of the fire extinguisher preventing access) | ✓
8 | Are there signs to make them easily noticeable? |  | ✗
Notes to be Added;
* Not Applicable This form has been prepared so that Health, Safety and Environment (HSE) inspections at construction sites are carried out by the relevant responsible persons.
The form filled in by the supervisor must be approved by the site chief and the project manager.
The form filled in by the site chief must be approved by the project manager
Site chiefs are expected to apply this form at the beginning of the project and once a month.
Supervisors are expected to fill in this form once a month at the sites where they are present.
Project EHS Manager
Full Name:
Date:- 03-SEP-2026
Signature:
Site Manager :
Full Name:Read Alnedawey
Date:- 03-SEP-2026
Signature:
Project Manager:
Full Name:Onur Ozvatan
Date:- 03-SEP-2026
Signature: